## Executive Summary
PulseCare Telehealth — Cybersecurity Risk Assessment
NIST CSF 2.0 / NIST SP 800-30 Aligned ¦ HIPAA Security Rule Crosswalk
Fictional Case Study for Portfolio Purposes — not based on any real client engagement or confidential information.
Organization Profile
• PulseCare Telehealth — mid-size telehealth platform, ~150 employees
• Handles PHI across patient scheduling, billing, and live video visits
• Cloud-hosted EHR integration; third-party billing clearinghouse and video vendor
Risk Summary (auto-calculated from Risk Register)
Critical risks identified: | 3
High risks identified: | 6
Medium risks identified: | 5
Low risks identified: | 1
Top Findings
• No centralized log correlation across EHR, telehealth video, and cloud infrastructure (RISK-10, Critical)
• MFA not enforced for clinical staff accessing EHR remotely (RISK-06, Critical)
• Third-party vendors onboarded without a formal BAA review process (RISK-03, Critical)
• No documented incident response plan for a confirmed PHI breach (RISK-12, High)
Methodology
Each risk scored as Likelihood (1-5) x Impact (1-5) = Risk Score (1-25). Score 1-4 = Low, 5-8 = Medium, 9-15 = High, 16-25 = Critical. Risks mapped to NIST CSF 2.0 functions and the corresponding HIPAA Security Rule safeguard.

## Risk Register
Risk ID | Date Identified | NIST CSF Function | Risk Category | Risk Description | Threat Source | Vulnerability | Existing Controls | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Rating | HIPAA Safeguard Mapping
RISK-01 | 2026-01-15 | Govern | Risk Management Strategy | No formal cybersecurity governance committee with executive sponsorship; security strategy decisions made ad hoc by IT Director without board-level visibility. | Internal process failure | No documented governance charter or risk oversight committee | Security issues escalated informally to IT Director | 3 | 4 | 12 | High
RISK-02 | 2026-01-15 | Govern | Roles, Responsibilities & Authorities | No designated HIPAA Security Officer distinct from the IT Director role, creating a conflict between operational IT duties and independent security oversight. | Organizational/governance gap | Security function combined with IT operations, no segregation of duties | IT Director handles day-to-day security tasks | 3 | 3 | 9 | High
RISK-03 | 2026-01-15 | Govern | Supply Chain Risk Management | Telehealth video vendor and billing clearinghouse were onboarded without a formal Business Associate Agreement (BAA) review process; both handle PHI. | Third-party compromise | No vendor security questionnaire, no BAA tracking log, no annual vendor review | Contracts reviewed by legal only, no security criteria | 4 | 5 | 20 | Critical
RISK-04 | 2026-01-15 | Identify | Asset Management | Asset inventory for the patient-facing mobile app and EHR integration points is maintained via a manually updated spreadsheet with no automated discovery. | Internal process gap | No continuous asset discovery across cloud and mobile environments | Manual spreadsheet updated quarterly | 2 | 3 | 6 | Medium
RISK-05 | 2026-01-15 | Identify | Risk Assessment | No formal, recurring risk assessment cadence exists; the organization's last full risk assessment was conducted over 18 months ago. | Internal process gap | No defined assessment schedule or ownership of the risk assessment process | Ad hoc assessments triggered only after incidents | 3 | 4 | 12 | High
RISK-06 | 2026-01-15 | Protect | Identity Management & Access Control | Multi-factor authentication is not enforced for clinical staff accessing the EHR remotely; MFA is only enforced for cloud admin and root accounts. | Credential theft / phishing | Inconsistent MFA policy across clinical vs. administrative accounts | MFA enforced for AWS root and Okta SSO admin only | 4 | 4 | 16 | Critical
RISK-07 | 2026-01-15 | Protect | Data Protection | PHI transmitted between the scheduling system and the third-party billing vendor lacks validated end-to-end encryption in transit. | Network interception | No encryption-in-transit validation process for vendor data flows | TLS used for primary EHR traffic only, billing flow unverified | 3 | 5 | 15 | High
RISK-08 | 2026-01-15 | Protect | Identity Management & Access Control | Periodic access reviews for EHR user accounts are not formally scheduled; two terminated contractor accounts were found still active during this assessment. | Insider threat / stale access | No defined quarterly or semi-annual access recertification process | Role-based access exists at point of provisioning only | 2 | 4 | 8 | Medium
RISK-09 | 2026-01-15 | Protect | Awareness & Training | Security awareness training is a single generic annual module for all staff, not tailored by role for clinical vs. billing personnel who handle PHI differently. | Phishing / social engineering | Training content not differentiated by PHI access level or job function | Annual company-wide training, no role-based modules | 1 | 2 | 2 | Low
RISK-10 | 2026-01-15 | Detect | Continuous Monitoring | No centralized log correlation exists across the EHR, telehealth video platform, and cloud infrastructure; logs remain siloed with no real-time alerting. | External attacker / undetected compromise | No SIEM or log aggregation layer across the three core systems | Logs exist independently per system, reviewed manually | 4 | 5 | 20 | Critical
RISK-11 | 2026-01-15 | Detect | Adverse Event Analysis | No formal process or defined use cases exist for detecting unauthorized PHI access; detection currently relies on manual, ad hoc log review. | External attacker / undetected compromise | No documented detection use cases or 24/7 monitoring coverage | Manual log review performed on an irregular basis | 3 | 4 | 12 | High
RISK-12 | 2026-01-15 | Respond | Incident Management | No documented incident response plan exists defining roles, escalation paths, or response procedures in the event of a confirmed PHI breach. | Any confirmed security incident | No IR plan, no defined severity classification, no on-call structure | Response coordinated informally by engineering leadership | 3 | 5 | 15 | High
RISK-13 | 2026-01-15 | Respond | Incident Response Reporting & Communication | No defined breach notification workflow exists mapped to HIPAA's 60-day individual notification requirement or applicable state breach laws. | Regulatory/compliance failure following incident | No documented notification workflow or legal escalation path | Legal team would be engaged informally if a breach occurred | 2 | 4 | 8 | Medium
RISK-14 | 2026-01-15 | Recover | Incident Recovery Plan Execution | A disaster recovery plan for the EHR and patient data exists on paper but has not been validated via a tabletop exercise in over 12 months. | System outage / disaster event | DR plan unvalidated, team unfamiliar with current execution steps | Documented DR plan; automated database backups | 2 | 4 | 8 | Medium
RISK-15 | 2026-01-15 | Recover | Data Backup & Recovery | Backup restoration procedures for the patient scheduling database have not been tested; recovery time and recovery point objectives are unconfirmed. | System outage / data loss event | No validated restore test; RTO/RPO targets undocumented | Automated nightly backups configured, restore untested | 2 | 3 | 6 | Medium

## POA&M
Risk ID | Risk Rating | Weakness | Remediation Action | Resources Required | Responsible Party | Target Completion | Status
RISK-10 | Critical | No centralized log correlation across EHR, video, and cloud | Deploy a SIEM (e.g., Wazuh) to aggregate logs from all three systems and build correlation alerting rules | SIEM platform, 1 engineer (40 hrs) | Security Engineer | 2026-04-30 | Not Started
RISK-06 | Critical | MFA not enforced for clinical staff EHR access | Extend existing Okta MFA policy to all EHR user roles; enforce via conditional access policy | Okta policy config (8 hrs) | IT Director | 2026-03-01 | Not Started
RISK-03 | Critical | Vendors onboarded without BAA review process | Implement a vendor security questionnaire and BAA tracking log; retroactively review existing vendor contracts | Legal + Security review (20 hrs) | Compliance Lead | 2026-03-15 | Not Started
RISK-12 | High | No documented incident response plan | Author a formal IR plan defining roles, severity tiers, and a PHI-breach-specific playbook aligned to NIST SP 800-61 | Security Engineer (24 hrs) | Security Officer | 2026-04-01 | Not Started
RISK-07 | High | Unvalidated encryption-in-transit for billing data flow | Validate TLS configuration on billing vendor integration; require evidence of encryption in vendor SOC 2 report | Engineering review (8 hrs) | Security Engineer | 2026-03-30 | Not Started
RISK-05 | High | No recurring risk assessment cadence | Establish an annual risk assessment policy with assigned ownership and calendar cadence | Compliance Lead (4 hrs) | Compliance Lead | 2026-02-28 | Not Started
RISK-11 | High | No formal detection process for unauthorized PHI access | Define detection use cases for the new SIEM (tied to RISK-10 remediation); document escalation runbook | Security Engineer (16 hrs) | Security Engineer | 2026-05-15 | Not Started
RISK-01 | High | No formal governance committee | Establish a quarterly security governance committee with executive sponsorship and documented charter | Executive sponsor time | CTO | 2026-03-01 | Not Started